## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3640071 | 68249 | ATM Project | 10 | ATM_1-10 | 292304 | Bug |  |  | 63779 | 1.1 | Withdrawal for more than account balance dispenses wrong amount of money | Function tested: Withdrawal more than account balance State: System has been started up with less than the maximum withdrawal amount in cash on hand; System is requesting a withdrawal amount Steps: Select 'Withdrawl', select a withdrawal amount greater than total amount balance. Expected outcome: System displays an appropriate message and asks customer if they would like to do another transaction. Actual outcome: System dispenses $20. | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 21, 2022 14:53 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:37 | 0 | 0 | Jan. 23, 2022 16:01 LAB1-1234 Found under MFT.
3637323 | 68249 | ATM Project | 1 | ATM_1-1 | 292304 | Bug |  |  | 63779 | 1.1 | Deposit: ATM steals $10 | Function tested: deposit State: On, card entered, deposit to any type of account. Steps: Select deposit to any kind of account, enter $100 (or any other number). Then insert envelope. Expected outcome: New balance = old balance + $100. Actual outcome: New balance = old balance + $90. $10 is missing from new balance. | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 20, 2022 17:26 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:25 | 0 | 0 | Jan. 23, 2022 16:04 LAB1-1234 Found again under MFT
3637343 | 68249 | ATM Project | 4 | ATM_1-4 | 292304 | Bug |  |  | 63779 | 1.1 | Unlimited $20 dispensing | Function: Any The initial state of the system : System is on and card is entered and validated Steps to reproduce: The system is turned on and the card is enterred and validated. Click 0 when 0 is not an option. Expected outcome: Nothing. Actual outcome: $20 dispensed from ATM with no fee. | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 20, 2022 17:41 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:25 | 0 | 0
3641488 | 68249 | ATM Project | 14 | ATM_1-14 | 292304 | Bug |  |  | 63779 | 1.1 | Transfer: ATM steals $0.50 | MFT: Function : Transfer The initial state of the system : System on, Card inserted Steps to reproduce: Transfer between two accounts (Eg. Savings to Checkings) Expected outcome: Full amount is transferred Actual outcome: Amount - $0.50 is transferred | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 23, 2022 16:11 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:25 | 0 | 0
3641492 | 68249 | ATM Project | 15 | ATM_1-15 | 292304 | Bug |  |  | 63779 | 1.1 | Clicking on MoneyMarket with card 1 dispenses $500 | MFT: Function : Inquiry System state: System is on, Inquiry menu screen Steps to reproduce: Log in to system with card 1, pin 42. Go to Inquiry Menu screen, click 2 Expected outcome : Account details for moneyMarket account type Actual outcome: Moneymarket account type doesn't exist for this system. Display receipt of balance inquiry for savings account. Dispenses $500 | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 23, 2022 16:15 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:25 | 0 | 0
3641495 | 68249 | ATM Project | 16 | ATM_1-16 | 292304 | Bug |  |  | 63779 | 1.1 | Inquiry Menu is incorrect | MFT: Function: Inquiry System state: System is on and on the Inquiry menu screen Steps to reproduce: Go to the Inquiry menu screen Expected outcome : 3 account types : Checkings, Savings, Moneymarket Actual outcome : only 2 account types : Checkings and MoneyMarket | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 23, 2022 16:18 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:25 | 0 | 0
3641508 | 68249 | ATM Project | 17 | ATM_1-3 | 292304 | Bug |  |  | 63779 | 1.1 | Withdrawal: System dispenses more money than requested | MFT: Function tested: System performs a legitimate withdrawal transaction properly State: The system is displaying the menu of withdrawal amounts Steps: Choose an amount that the system currently has and is not greater than the account balance which is the chequing account. Expected outcome: System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) Actual outcome: System dispenses the next highest option amount. | 3 | Resolved | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 23, 2022 16:41 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:25 | 0 | 0
3641525 | 68249 | ATM Project | 18 | ATM_1-18 | 292304 | Bug |  |  | 63779 | 1.1 | Deposit: ATM steals $0.10 | Function tested: deposit State: On, card entered, deposit to any type of account. Steps: Select deposit to any kind of account, enter $100 (or any other number). Then insert envelope. Expected outcome: New balance = old balance + $100. Actual outcome: New balance = old balance + $99.90. $0.10 is missing from new balance. | 1 | Open | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 23, 2022 17:14 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:24 | 0 | 0
3641480 | 68249 | ATM Project | 13 | ATM_1-13 | 292304 | Bug |  |  | 63778 | 1.0 | Connection to bank unclear on system startup | MFT: Function: Connection to bank The initial state of the system : System is on and is idle, i.e., not already serving a customer Steps to reproduce: The system is turned on and the log is checked Expected outcome: An indication that the ATM is connected to the bank Actual outcome: No indication, logs are blank | 2 | In Progress | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 23, 2022 15:59 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:22 | 0 | 0 | Jan. 23, 2022 17:22 LAB1-1234 Defect still exists in 1.1
3640087 | 68249 | ATM Project | 12 | ATM_1-12 | 292304 | Bug |  |  | 63778 | 1.0 | PIN is asked multiple times | Function tested: Invalid PIN extension State: System is asking for entry of PIN Steps: Select 'Insert card', enter '2' for card number, enter invalid pin, enter the correct pin. OR Select 'Insert card', enter '2' for card number, enter invalid pin, enter the invalid pin again, enter the correct pin Expected outcome: Original transaction completes successfully Actual outcome: User is asked to enter PIN again, even if the new PIN they entered is correct. | 2 | In Progress | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 21, 2022 15:07 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:22 | 0 | 0 | Jan. 23, 2022 16:00 LAB1-1234 Found it again while MFT. | Jan. 23, 2022 17:22 LAB1-1234 Defect still exists in 1.1
3640061 | 68249 | ATM Project | 9 | ATM_1-9 | 292304 | Bug |  |  | 63778 | 1.0 | Invalid card is accepted | Function tested: Customer enters card number State: System is on and requesting a card number. Steps: Insert card, enter card number 3. Expected outcome: Card number should not be accepted. Actual outcome: Card number is accepted and system asks for PIN. | 2 | In Progress | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 21, 2022 14:46 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:18 | 0 | 0 | Jan. 23, 2022 16:54 LAB1-1234 Found again under MFT | Jan. 23, 2022 17:18 LAB1-1234 Defect still exists in 1.1
3637354 | 68249 | ATM Project | 5 | ATM_1-5 | 292304 | Bug |  |  | 63778 | 1.0 | Deposited money isn't available | Function tested: deposit State: On, card entered Steps: Select 'deposit' to any account type, and deposit $100. Expected outcome: Upon executing a balance inquiry for the same account, the old total balance + $100 should be the 'total balance', and the old available balance + $100 should be the 'available balance'. Actual outcome: Available balance = old available balance, total balance = old total balance + $100. | 2 | In Progress | 3 | Normal | [6 empty] | 319607 | LAB1-1234 | Jan. 20, 2022 17:48 |  | 319607 | LAB1-1234 | Jan. 23, 2022 17:18 | 0 | 0 | Jan. 23, 2022 16:59 LAB1-1234 Found again on MFT | Jan. 23, 2022 17:18 LAB1-1234 Defect still exists in 1.1